## Overall Gantt
TASK ID | TASK TITLE | OWNER | START | DUE | DAYS | % DONE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
SECTION 2 — ARCHITECTURE & SYSTEM DESIGN
ARCH-01 | Finalize SRS and requirements baseline document | BA / Architect | 2026-03-16 | 2026-03-18 | 3 | 100%
ARCH-02 | Objective 2 – architectural pattern selection and justification | System Architect | 2026-03-16 | 2026-03-17 | 2 | 100% | bar: WEEK 2 M to WEEK 2 T
ARCH-03 | System context diagram (Level 0 DFD) and actor boundary | System Architect | 2026-03-17 | 2026-03-17 | 1 | 100%
ARCH-04 | Level 1 DFD – data flows across all CMS subsystems | System Architect | 2026-03-17 | 2026-03-18 | 2 | 100% | bar: WEEK 2 T to WEEK 2 W
ARCH-05 | Entity Relationship Diagram (ERD) – all MongoDB collections | Backend Lead | 2026-03-18 | 2026-03-19 | 2 | 100%
ARCH-06 | MongoDB schema design – User, Team, OTP, RefreshToken collections | Backend Lead | 2026-03-18 | 2026-03-19 | 2 | 100% | bar: WEEK 2 W to WEEK 2 R
ARCH-07 | MongoDB schema design – Project, Submission, Notification, Audit | Backend Lead | 2026-03-19 | 2026-03-20 | 2 | 100%
ARCH-08 | MongoDB indexing strategy (compound, TTL, text indexes) | Backend Lead | 2026-03-20 | 2026-03-20 | 1 | 80% | bar: WEEK 2 F
ARCH-09 | Use case diagram (all 4 roles – complete system scope) | System Architect | 2026-03-23 | 2026-03-24 | 2 | 100%
ARCH-10 | Sequence diagrams – auth, title submission, document upload flows | System Architect | 2026-03-24 | 2026-03-25 | 2 | 80% | bar: WEEK 3 T to WEEK 3 W
ARCH-11 | REST API contract – auth, user, team endpoints (OpenAPI spec) | Backend Lead | 2026-03-23 | 2026-03-24 | 2 | 80%
ARCH-12 | REST API contract – project, submission, review endpoints | Backend Lead | 2026-03-24 | 2026-03-25 | 2 | 70% | bar: WEEK 3 T to WEEK 3 W
ARCH-13 | REST API contract – plagiarism, evaluation, archive endpoints | Backend Lead | 2026-03-25 | 2026-03-26 | 2 | 100%
ARCH-14 | Backend feature-module decomposition and service boundary diagram | System Architect | 2026-03-25 | 2026-03-26 | 2 | 80% | bar: WEEK 3 W to WEEK 3 R
ARCH-15 | UI wireframes – Student dashboard and all workflow pages | UI/UX | 2026-03-23 | 2026-03-25 | 3 | 90%
ARCH-16 | UI wireframes – Adviser and Panelist dashboard pages | UI/UX | 2026-03-25 | 2026-03-26 | 2 | 90% | bar: WEEK 3 W to WEEK 3 R
ARCH-17 | UI wireframes – Instructor admin dashboard and report pages | UI/UX | 2026-03-26 | 2026-03-27 | 2 | 80%
ARCH-18 | Component hierarchy and role-based route navigation map | UI/UX | 2026-03-26 | 2026-03-27 | 2 | 70% | bar: WEEK 3 R to WEEK 3 F
ARCH-19 | Third-party integration contracts (S3, Copyleaks, Redis, GDrive) | System Architect | 2026-03-25 | 2026-03-26 | 2 | 70%
ARCH-20 | Security threat model and OWASP mitigation matrix | Security Lead | 2026-03-27 | 2026-03-27 | 1 | 60% | bar: WEEK 3 F
SECTION 3 — INFRASTRUCTURE SETUP
INFRA-01 | Docker Compose dev environment – service linking verification | DevOps | 2026-03-23 | 2026-03-24 | 2 | 100%
INFRA-02 | Environment variable schema and .env.example secrets management | DevOps | 2026-03-24 | 2026-03-24 | 1 | 100% | bar: WEEK 3 T
INFRA-03 | MongoDB Atlas cluster setup, connection string and replica verify | DevOps | 2026-03-24 | 2026-03-25 | 2 | 100%
INFRA-04 | Redis server config and BullMQ queue/worker initialization | DevOps / Backend | 2026-03-25 | 2026-03-26 | 2 | 100% | bar: WEEK 3 W to WEEK 3 R
INFRA-05 | AWS S3 bucket creation, IAM policy and CORS configuration | DevOps | 2026-03-25 | 2026-03-26 | 2 | 100%
INFRA-06 | AWS pre-signed upload/download URL flow verification | DevOps / Backend | 2026-03-26 | 2026-03-27 | 2 | 90% | bar: WEEK 3 R to WEEK 3 F
INFRA-07 | Custom plagiarism engine (FastAPI + ChromaDB + Celery) setup | Backend Integ. | 2026-03-26 | 2026-03-27 | 2 | 100%
INFRA-08 | Transactional email (Mailtrap dev / SendGrid prod) configuration | DevOps / Backend | 2026-03-27 | 2026-03-27 | 1 | 80% | bar: WEEK 3 F
INFRA-09 | ESLint, Prettier, Husky and lint-staged pre-commit hooks | DevOps | 2026-03-23 | 2026-03-24 | 2 | 100%
INFRA-10 | Git branching model enforcement (main/develop/feature/* rules) | DevOps | 2026-03-24 | 2026-03-24 | 1 | 100% | bar: WEEK 3 T
INFRA-11 | GitHub Actions CI pipeline (lint + test on every PR) | DevOps | 2026-03-26 | 2026-03-27 | 2 | 70%
INFRA-12 | Monorepo npm workspace dependency audit and security patch | DevOps | 2026-03-27 | 2026-03-27 | 1 | 70% | bar: WEEK 3 F
INFRA-13 | Nginx reverse proxy config (dev + prod) and CORS header rules | DevOps | 2026-03-30 | 2026-03-31 | 2 | 60%
INFRA-14 | Google Drive service account credentials and API scope setup | Backend Integ. | 2026-03-30 | 2026-04-01 | 3 | 50% | bar: WEEK 4 M to WEEK 4 W
SECTION 4 — BACKEND FOUNDATION
BE-FOUND-01 | Express server baseline – helmet, cors, cookieParser, bodyParser | Backend | 2026-03-30 | 2026-03-31 | 2 | 100%
BE-FOUND-02 | Mongoose connection with retry logic and graceful shutdown | Backend | 2026-03-30 | 2026-03-30 | 1 | 100% | bar: WEEK 4 M
BE-FOUND-03 | Centralized error handler (AppError class + catchAsync wrapper) | Backend | 2026-03-30 | 2026-03-31 | 2 | 100%
BE-FOUND-04 | Request validation middleware (Joi schemas per route group) | Backend | 2026-03-31 | 2026-04-01 | 2 | 80% | bar: WEEK 4 T to WEEK 4 W
BE-FOUND-05 | Audit log middleware and AuditLog Mongoose model | Backend | 2026-03-31 | 2026-04-01 | 2 | 80%
BE-FOUND-06 | Rate limiter per route group (auth: 10/15 min, API: 100/15 min) | Backend / Sec. | 2026-04-01 | 2026-04-01 | 1 | 70% | bar: WEEK 4 W
BE-FOUND-07 | File MIME magic-bytes validation middleware (server-side strict) | Backend / Sec. | 2026-04-01 | 2026-04-02 | 2 | 70%
BE-FOUND-08 | BullMQ queue setup (plagiarism-check + email-dispatch workers) | Backend / Infra | 2026-04-01 | 2026-04-02 | 2 | 100% | bar: WEEK 4 W to WEEK 4 R
BE-FOUND-09 | Email BullMQ worker (Nodemailer, retry policy, dead-letter queue) | Backend / Infra | 2026-04-02 | 2026-04-03 | 2 | 50%
BE-FOUND-10 | Socket.IO base setup, namespace config and auth handshake | Backend / Infra | 2026-04-02 | 2026-04-03 | 2 | 40% | bar: WEEK 4 R to WEEK 4 F
BE-FOUND-11 | Storage service (S3 wrapper – upload, download, delete, presign) | Backend / Infra | 2026-04-02 | 2026-04-03 | 2 | 50%
SECTION 5 — AUTHENTICATION & USER MODULE
AUTH-01 | User Mongoose model (schema, indexes, static/instance methods) | Backend | 2026-03-30 | 2026-03-31 | 2 | 90% | bar: WEEK 4 M to WEEK 4 T
AUTH-02 | OTP model (TTL index 10-min expiry, 6-digit secure generator) | Backend | 2026-03-31 | 2026-03-31 | 1 | 90%
AUTH-03 | RefreshToken model with rotation tracking and revocation list | Backend | 2026-04-01 | 2026-04-01 | 1 | 80% | bar: WEEK 4 W
AUTH-04 | Register endpoint – hash password, create user, dispatch OTP email | Backend | 2026-04-01 | 2026-04-02 | 2 | 70%
AUTH-05 | OTP verify and account activation endpoint | Backend | 2026-04-02 | 2026-04-02 | 1 | 60% | bar: WEEK 4 R
AUTH-06 | Login endpoint (bcrypt compare, JWT access token + refresh cookie) | Backend | 2026-04-02 | 2026-04-03 | 2 | 60%
AUTH-07 | JWT authenticate middleware (extract, verify, attach user to req) | Backend | 2026-04-03 | 2026-04-03 | 1 | 60% | bar: WEEK 4 F
AUTH-08 | Refresh token rotation endpoint (revoke old pair, issue new pair) | Backend | 2026-04-03 | 2026-04-04 | 2 | 50%
AUTH-09 | Logout endpoint (clear cookies, server-side refresh revocation) | Backend | 2026-04-04 | 2026-04-04 | 1 | 50%
AUTH-10 | RBAC authorize middleware (role-hierarchy, route-level guards) | Backend | 2026-04-04 | 2026-04-07 | 4 | 50%
AUTH-11 | Password reset flow (request OTP -> verify -> set new password) | Backend | 2026-04-04 | 2026-04-07 | 4 | 40% | bar: WEEK 5 M to WEEK 5 T
AUTH-12 | Get / update user profile endpoint with avatar S3 upload | Backend | 2026-04-06 | 2026-04-07 | 2 | 30%
AUTH-13 | Instructor: create/list/update role/deactivate user (admin CRUD) | Backend | 2026-04-07 | 2026-04-09 | 3 | 20% | bar: WEEK 5 T to WEEK 5 R
SECTION 11 — NOTIFICATION MODULE
NOTIF-01 | Notification model (recipient, type, metadata, read status, ts) | Backend | 2026-04-08 | 2026-04-08 | 1 | 10%
NOTIF-02 | Notification service helper (createNotification used by all modules) | Backend | 2026-04-08 | 2026-04-09 | 2 | 5% | bar: WEEK 5 W to WEEK 5 R
NOTIF-03 | Get notifications endpoint – paginated with unread count | Backend | 2026-04-09 | 2026-04-09 | 1 | 5%
NOTIF-04 | Mark notification read / mark-all-read endpoint | Backend | 2026-04-09 | 2026-04-10 | 2 | 0% | bar: WEEK 5 R to WEEK 5 F
NOTIF-05 | Socket.IO real-time notification push (emit on notif create event) | Backend | 2026-04-11 | 2026-04-12 | 2 | 0%
NOTIF-06 | Email notification templates (upload, approval, rejection, due) | Backend | 2026-04-12 | 2026-04-14 | 3 | 0% | bar: WEEK 6 M to WEEK 6 T
NOTIF-07 | Deadline proximity cron job (24h / 48h reminder auto-dispatch) | Backend | 2026-04-21 | 2026-04-22 | 2 | 0%
SECTION 12 — FRONTEND CORE SHELL
FE-SHELL-01 | Vite + React 18 config audit and workspace dependency resolution | Frontend | 2026-03-30 | 2026-03-30 | 1 | 100% | bar: WEEK 4 M
FE-SHELL-02 | Tailwind CSS configuration with strict tw- prefix enforcement | Frontend | 2026-03-30 | 2026-03-31 | 2 | 100%
FE-SHELL-03 | React Router v6 route structure (public, protected, role-guard) | Frontend | 2026-03-31 | 2026-04-01 | 2 | 80% | bar: WEEK 4 T to WEEK 4 W
FE-SHELL-04 | Axios instance with interceptors (token refresh + error norm.) | Frontend | 2026-04-01 | 2026-04-02 | 2 | 80%
FE-SHELL-05 | Zustand auth store (user, token, role, isAuthenticated state) | Frontend | 2026-04-02 | 2026-04-03 | 2 | 70% | bar: WEEK 4 R to WEEK 4 F
FE-SHELL-06 | React Query provider and global config (staleTime, retry, gc) | Frontend | 2026-04-03 | 2026-04-03 | 1 | 70%
FE-SHELL-07 | Dark/light mode toggle with OS preference detection | Frontend | 2026-04-03 | 2026-04-04 | 2 | 80% | bar: WEEK 4 F
FE-SHELL-08 | shadcn/ui component library integration and brand theming | Frontend | 2026-04-04 | 2026-04-07 | 4 | 70%
FE-SHELL-09 | Global error boundary component and fallback UI | Frontend | 2026-04-07 | 2026-04-08 | 2 | 60% | bar: WEEK 5 T to WEEK 5 W
FE-SHELL-10 | Role-aware layout components (Student, Adviser, Panelist, Instr.) | Frontend | 2026-04-08 | 2026-04-10 | 3 | 50%
FE-SHELL-11 | Shared UI atoms: Button, Input, Badge, Toast, Modal, Spinner | Frontend | 2026-04-09 | 2026-04-10 | 2 | 50% | bar: WEEK 5 R to WEEK 5 F
SECTION 19 — INTEGRATION & SECURITY HARDENING
INT-01 | E2E auth flow (register -> OTP -> login -> refresh -> logout) | Integration | 2026-04-24 | 2026-04-24 | 1 | 0%
INT-02 | E2E team flow (create -> invite -> accept -> lock roster) | Integration | 2026-04-24 | 2026-04-25 | 2 | 0% | bar: WEEK 7 F
INT-03 | E2E submission flow (upload -> plagiarism -> review -> approve) | Integration | 2026-04-25 | 2026-04-26 | 2 | 0%
INT-04 | Cross-module API stabilization and OpenAPI contract verification | Integration | 2026-04-25 | 2026-04-26 | 2 | 0%
INT-05 | Security hardening audit (OWASP top-10, injection, XSS, CSRF) | Sec. / Backend | 2026-04-26 | 2026-04-27 | 2 | 0%
INT-06 | API rate limiter stress test – auth/upload endpoint tuning | Sec. / Backend | 2026-04-27 | 2026-04-27 | 1 | 0% | bar: WEEK 8 M
INT-07 | Redis caching layer for hot reads (session, project queries) | Backend | 2026-04-27 | 2026-04-28 | 2 | 0%
INT-08 | Pagination and cursor-based query optimization on all list routes | Backend | 2026-04-27 | 2026-04-28 | 2 | 0% | bar: WEEK 8 M to WEEK 8 T
INT-09 | Accessibility audit (ARIA labels, keyboard nav, color contrast) | Frontend / QA | 2026-04-28 | 2026-04-29 | 2 | 0%
INT-10 | Responsive design audit (mobile, tablet, desktop breakpoints) | Frontend / QA | 2026-04-28 | 2026-04-29 | 2 | 0% | bar: WEEK 8 T to WEEK 8 W
SECTION 20 — TESTING & QA
TEST-01 | Unit tests – auth service (register, login, OTP, JWT, refresh) | QA / Dev | 2026-04-24 | 2026-04-25 | 2 | 0%
TEST-02 | Unit tests – team service (create, invite, accept, lock, orphan) | QA / Dev | 2026-04-24 | 2026-04-25 | 2 | 0% | bar: WEEK 7 F
TEST-03 | Unit tests – project service (title, similarity, phase advance) | QA / Dev | 2026-04-25 | 2026-04-26 | 2 | 0%
TEST-04 | Unit tests – submission service (upload, versioning, locking) | QA / Dev | 2026-04-25 | 2026-04-26 | 2 | 0%
TEST-05 | Unit tests – plagiarism worker (mock Copyleaks, score-map) | QA / Dev | 2026-04-26 | 2026-04-27 | 2 | 0%
TEST-06 | Integration tests – auth routes (403/401 RBAC assertions) | QA | 2026-04-26 | 2026-04-27 | 2 | 0% | bar: WEEK 8 M
TEST-07 | Integration tests – team and project routes | QA | 2026-04-27 | 2026-04-28 | 2 | 0%
TEST-08 | Integration tests – submission, review, and evaluation routes | QA | 2026-04-27 | 2026-04-28 | 2 | 0% | bar: WEEK 8 M to WEEK 8 T
TEST-09 | End-to-end UI tests (Playwright – full happy path per role) | QA | 2026-04-28 | 2026-04-30 | 3 | 0%
TEST-10 | Bug fixing and regression cycle (all critical and high defects) | Dev Team | 2026-04-29 | 2026-04-30 | 2 | 0% | bar: WEEK 8 W to WEEK 8 R
SECTION 21 — DEPLOYMENT & DOCUMENTATION
DEPLOY-01 | Docker Compose production config (multi-stage Dockerfile build) | DevOps | 2026-04-27 | 2026-04-28 | 2 | 0%
DEPLOY-02 | Nginx production config, SSL termination and LAN routing | DevOps | 2026-04-28 | 2026-04-28 | 1 | 0% | bar: WEEK 8 T
DEPLOY-03 | Production environment variables and secrets rotation procedure | DevOps | 2026-04-28 | 2026-04-29 | 2 | 0%
DEPLOY-04 | Database backup, restore and point-in-time recovery procedure | DevOps | 2026-04-29 | 2026-04-29 | 1 | 0% | bar: WEEK 8 W
DEPLOY-05 | Deployment runbook and rollback procedure document | DevOps / PM | 2026-04-29 | 2026-04-30 | 2 | 0%
LEGEND
Completed (100%)
In Progress (> 0%)
Planned (0%)
Section Header