## Simple Gantt Chart - EX
CAPSTONE PROJECT AND RESEARCH 2 GANTT CHART
CAPSTONE PROJECT TITLE | Project Workspace: Capstone Management System with Plagiarism Checker
NAME OF STUDENTS | Añedez, Patrick Josh, Antipuesto, Throylan, Bautista, Steven Joe, Canoy, Chijay
NAME OF ADVISER | Glaiza Mae A. Libe
SECTION CODE / SCHEDULE | T87 / TF 10:00AM-12:30PM
OVERALL ACCOMPLISHMENT | 40.88% | as of | 2026-03-19
[8 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | % OF TASK |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE |  | M | T | W | T | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
| Phase 1: Data Gathering & Analysis | [6 empty] | WEEK 1 M: Planning; WEEK 2 M: Data collection; WEEK 3 M: Annotation & validation; WEEK 4 M: Initial training; WEEK 5 M: Testing & refinement; WEEK 6 M: Integration & real-time detection; WEEK 7 M: Crushing risk logic; WEEK 8 M: Health & analytics; WEEK 9 M: Prediction validation; WEEK 10 M: Integration; WEEK 11 M: Testing & optimization; WEEK 12 M: Documentation & defense prep
| Document Analysis: Review university policies and capstone guidelines. | [5 empty] | 0
| List the manual steps currently used to check for plagiarism. | Antipuesto, Throylan | 2026-02-11 |  | -46064 | 80% | bar: WEEK 2 M to WEEK 2 T; WEEK 3 M to WEEK 3 T
| Collect current University Capstone formatting guidelines. | Antipuesto, Throylan | 2026-02-11 |  | -46064 | 80% | bar: WEEK 2 M to WEEK 2 T; WEEK 3 M to WEEK 3 T
| Identify specific metadata required for archiving (e.g., Year, Keywords, Adviser name). | Antipuesto, Throylan | 2026-02-11 |  | -46064 | 80% | bar: WEEK 2 M to WEEK 2 T; WEEK 3 M to WEEK 3 T
| Key Informant Interviews: Consult with advisers and panel members. | [5 empty] | 0
| Draft interview questions for the Capstone Coordinator and 2–3 Panelists. | Antipuesto, Throylan |  |  |  | 90% | bar: WEEK 2 M to WEEK 2 W; WEEK 3 M to WEEK 3 T
| Summarize interview notes into a list of "Must-Have" features. | Antipuesto, Throylan |  |  |  | 100%
| Schedule and conduct interviews (focus on "pain points" in the current process). | Antipuesto, Throylan |  |  |  | 20%
3 | User Surveys: Conduct surveys with 3rd and 4th-year BSIT/BSEMC students. | [5 empty] | 0
| Draft interview questions for the Capstone Coordinator and 2–3 Panelists. | Antipuesto, Throylan |  |  |  | 50%
| Summarize interview notes into a list of "Must-Have" features. | Antipuesto, Throylan |  |  |  | 80%
| Schedule and conduct interviews (focus on "pain points" in the current process). | Antipuesto, Throylan |  |  |  | 80%
6 | SRS (System Requirements Specification) | [5 empty] | 0
7 | List all Functional Requirements (e.g., "Student can upload .docx"). | Antipuesto, Throylan | 2026-02-11 |  | -46064 | 100% | 1
8 | List Non-Functional Requirements (e.g., "System must load within 3 seconds"). | Antipuesto, Throylan | 2026-02-10 |  | -46063 | 100% | 1
9 | Get a formal "Ok" or sign-off from your adviser on these requirements. | Añedez, Patrick Josh | 2026-02-10 |  | -46063 | 0% | 0
| Phase 2: System Design | [5 empty] | 0
3 | System Architecture
| Set up the folder structure for the Client (React) and Server (Node/Express). | Añedez, Patrick Josh | 2026-02-11 | 2026-02-17 | 6 | 100%
| Define the folder path for local file storage or cloud integration. | Añedez, Patrick Josh | 2026-02-11 | 2026-02-17 | 6 | 100%
| Database Schema Design | [5 empty] | 0
| Create User Schema (Name, Email, Role: Student/Adviser/Coordinator). | Añedez, Patrick Josh |  |  |  | 40% | bar: WEEK 2 T to WEEK 3 M; WEEK 4 T to WEEK 5 M; WEEK 5 W to WEEK 6 M; WEEK 7 T to WEEK 8 M; WEEK 8 W to WEEK 9 M; WEEK 10 W to WEEK 11 T; WEEK 11 R to WEEK 12 M
4 | Create Project Schema (Title, Abstract, Team Members, Status). | Añedez, Patrick Josh |  |  |  | 40% | bar: WEEK 2 T to WEEK 3 M; WEEK 4 W to WEEK 5 T; WEEK 5 R to WEEK 6 M; WEEK 7 T to WEEK 8 M; WEEK 8 W; WEEK 8 F; WEEK 10 M to WEEK 10 F; WEEK 11 T; WEEK 11 R to WEEK 12 M
| Create Submission Schema (File Link, Plagiarism Score, Timestamp, Version #). | Añedez, Patrick Josh |  |  |  | 40% | bar: WEEK 2 T to WEEK 3 M; WEEK 4 W to WEEK 5 T; WEEK 5 R to WEEK 6 M; WEEK 7 W to WEEK 8 T; WEEK 8 R to WEEK 8 F; WEEK 10 M to WEEK 10 F; WEEK 11 T to WEEK 12 M
5 | UI/UX Design | [5 empty] | 0
6 | Create a low-fidelity wireframe for the System | Canoy, Chijay | 2026-02-10 |  | -46063 | 20% | 0
7 | Design high-fidelity Figma prototypes for Student vs. Coordinator views. | Canoy, Chijay |  |  |  | 20%
8 | Design the "Document Vault" interface (how the archives will look). | Canoy, Chijay |  |  |  | 40% | 0
9 | API Integration Design | [5 empty] | 0
15 | Register for a Copyleaks API key and review the webhook documentation. | Añedez, Patrick Josh |  |  |  | 0% | 0
| Set up a Google Cloud Console project to get OAuth2 credentials for Google Docs. | Añedez, Patrick Josh |  |  |  | 100%
16 | Map out the data flow: User Uploads → Google Docs → Copyleaks → Database Update. | Añedez, Patrick Josh |  |  |  | 50% | 0
Technical Architecture & Security
| Defining the MERN stack flow, including a 17-controller MVC backend and an 8-page React frontend. | Añedez, Patrick Josh |  |  |  | 100%
| Designing a secure JWT-based authentication system for four specific roles (Student, Adviser, Panelist, Coordinator). | Añedez, Patrick Josh |  |  |  | 100%
| Building a "State Machine" to track capstone progress from topic selection all the way to final archiving. | Añedez, Patrick Josh |  |  |  | 100%
| Planning for XSS/CORS protection and a zero-cost deployment strategy using Vercel, Render, and MongoDB Atlas. | Añedez, Patrick Josh |  |  |  | 20%
| Database & Data Modeling | [5 empty] | 0
| Core Entity Modeling: Designing schemas for Users (supporting 4 distinct roles), Projects (complex structure including versioning, Google Docs integration, and state machines), Teams (group management), and Topics (marketplace data). | Añedez, Patrick Josh |  |  |  | 50%
| Workflow & Operations: Creating schemas to handle Deadlines (phase-specific), Title Change Requests (approval flow), and Notifications (25+ types). | Añedez, Patrick Josh |  |  |  | 50%
| Security & Auditing: Implementing PendingRegistration (for OTP/TTL verification) and rigorous logging via WorkflowLogs and AuthLogs. | Añedez, Patrick Josh |  |  |  | 50%
| Structural Definition: The phase concludes with the creation of a comprehensive Entity Relationship Diagram (ERD) to map relationships and an Indexing Strategy to ensure query performance. | Añedez, Patrick Josh |  |  |  | 50%
| Backend Development | [5 empty] | 0
| Designing 10+ MongoDB collections (Users, Projects, Teams, Topics, Notifications, etc.) to handle complex relationships. | Añedez, Patrick Josh |  |  |  | 100%
| Creating an Entity Relationship Diagram (ERD) and defining indexing strategies to ensure the system remains fast as the archive grows. | Añedez, Patrick Josh |  |  |  | 60%
| UI/UX & User Experience | [5 empty] | 0
| Component-Driven Design: Establishing a design system using Tailwind CSS and Shadcn UI. | Añedez, Patrick Josh |  |  |  | 100%
| Role-Specific Dashboards: Creating detailed Figma wireframes and interactive prototypes for all four user types to ensure the interface meets their specific needs. | Canoy, Chijay |  |  |  | 60%
| Stakeholder Validation: Using the prototypes to get early feedback from advisers before writing the first line of frontend code. | Canoy, Chijay |  |  |  | 60% | 0
| Integration & Infrastructure Setup | [5 empty] | 0
| API Blueprints: Mapping out 80+ RESTful endpoints and specialized integrations for Google Drive/Docs (for live editing) and Copyleaks (for plagiarism). | Añedez, Patrick Josh |  |  |  | 30%
| Environment Readiness: Setting up the GitHub repository, Google Cloud Console, and MongoDB clusters. | Añedez, Patrick Josh |  |  |  | 100%
| Proof of Concept (PoC): Running "stress tests" on critical features—like streaming large files to Google Drive within Render’s 512MB RAM limit—to prove the tech works before full-scale development. | Añedez, Patrick Josh |  |  |  | 0%
| Academic Documentation | [5 empty] | 0
| Methodology (Chapter 3): Translating these technical plans into a formal manuscript that explains the research design, development methodology (Agile), and evaluation criteria. | Antipuesto, Throylan |  |  |  | 0%
| Phase 3: Development | [5 empty] | 0
| The Backend Engine (MVC Logic) | [5 empty] | 0
| Database & Models: Implementing 10+ Mongoose schemas to handle complex relationships between users, teams, and projects. | Añedez, Patrick Josh |  |  |  | 30%
| The Controller Suite: Developing 17+ controllers to manage specific logic, such as the State Machine for project progress, gap analysis for research topics, and automated notifications. | Añedez, Patrick Josh |  |  |  | 60%
| Security & Auth: Implementing JWT-based protection, Role-Based Access Control (RBAC), and OTP verification for secure registration. | Añedez, Patrick Josh |  |  |  | 70%
| The Frontend Experience (React & Dashboards) | [5 empty] | 0
| State & Theme Management: Setting up global contexts for authentication and dark/light mode. | Añedez, Patrick Josh |  |  |  | 100%
| Role-Specific Dashboards: Building four distinct experiences (Student, Adviser, Panelist, and Coordinator) that dynamically show different tools based on the logged-in user. | Añedez, Patrick Josh |  |  |  | 40%
| Component Library: Assembling 30+ reusable components using Tailwind CSS and Shadcn UI for a consistent, professional look. | Añedez, Patrick Josh |  |  |  | 100%
| External API Ecosystem | [5 empty] | 0
| Google Drive & Docs: Implementing the streaming upload logic (to handle the 512MB RAM limit) and enabling real-time document creation and sharing directly through your app. | Añedez, Patrick Josh |  |  |  | 60%
| Communication: Wiring Nodemailer to Gmail SMTP to handle real-time alerts for deadlines and approvals. | Añedez, Patrick Josh |  |  |  | 100%
| Plagiarism: Setting up a "plug-and-play" service for future Copyleaks integration. | Añedez, Patrick Josh |  |  |  | 0%
| The "Document Vault" & Versioning | [5 empty] | 0
| Versioning: Building the logic to track every version of a chapter submission, including who uploaded it and when. | Añedez, Patrick Josh |  |  |  | 70%
| Document Locking: Implementing "pessimistic locking" so that files cannot be edited by multiple people simultaneously, preventing data loss. | Añedez, Patrick Josh |  |  |  | 70%
| Archiving: Creating the "Read-Only" logic for final approved manuscripts to ensure they remain official and unalterable. | Añedez, Patrick Josh |  |  |  | 70%
| Quality Assurance | [5 empty] | 0
| Performance: Setting up database indexing in MongoDB Atlas to ensure search and filtering remain fast as the repository grows. | Añedez, Patrick Josh |  |  |  | 0%
| Documentation: Generating API contracts (Swagger/OpenAPI) and a comprehensive setup guide for future maintainers. | Añedez, Patrick Josh |  |  |  | 0%
| Phase 4: Testing | [5 empty] | 0
| Core Technical Testing (Unit & Integration) | [5 empty] | 0
| Jest Framework: Setting up a dedicated testing environment using a MongoDB memory server to test logic without polluting your real database. | Canoy, Chijay |  |  |  | 20%
| Model & Controller Validation: Writing tests to ensure every field (like email uniqueness or chapter versioning) and every route (like registration or team locking) behaves exactly as expected. | Canoy, Chijay |  |  |  | 20%
| End-to-End Flows: Testing "The Big Three" workflows: Auth (login to logout), Project Lifecycle (proposal to archive), and Team Formation. | Canoy, Chijay |  |  |  | 20%
| RBAC Verification: Proving that a Student cannot "accidentally" access Coordinator settings. | Canoy, Chijay |  |  |  | 0%
| Functional & Performance Testing | [5 empty] | 0
| Black-Box Testing: Testing features like file uploads and notifications from a user perspective without looking at the code. | Bautista, Steven Joe |  |  |  | 0%
| API Mastery: Using Postman to validate all 80+ endpoints, ensuring they return the correct status codes and error messages. | Bautista, Steven Joe |  |  |  | 0%
| Constraint Stress-Testing: Since you're on Render’s free tier (512MB RAM), you'll be testing how the Google Drive streaming handles 25MB files to ensure the server doesn't crash under pressure. | Bautista, Steven Joe |  |  |  | 0%
| Responsiveness: Verifying the dashboard looks as good on a smartphone as it does on a desktop. | Bautista, Steven Joe |  |  |  | 0%
| Plagiarism & Security Guardrails | [5 empty] | 0
| Controlled Corpus: Using a set of "dummy" documents with known plagiarism levels to verify your system correctly processes and displays similarity scores. | Bautista, Steven Joe |  |  |  | 0%
| Attack Simulation: Testing for common vulnerabilities like NoSQL injection, XSS (scripting in comments), and brute-force login attempts. | Bautista, Steven Joe |  |  |  | 0%
| Audit Trail: Ensuring the WorkflowLog captures every single document access or status change for accountability. | Bautista, Steven Joe |  |  |  | 0%
| The Final Stretch (Documentation & Defense) | [5 empty] | 0
| User Manuals: Creating step-by-step guides for Students, Advisers, and Coordinators so they aren't lost on day one. | Bautista, Steven Joe |  |  |  | 0%
| Demo Scripting: Orchestrating a "perfect" walkthrough of the system to show off the most impressive features during the defense. | Bautista, Steven Joe |  |  |  | 0%
| The Defense Cycle: Preparing slides, rehearsing with your adviser, and—most importantly—having a structured way to track and implement the panel's feedback after the big day. | Bautista, Steven Joe |  |  |  | 0%
| Phase 5: EVALUATION & CLOSING | [5 empty] | 0
| User Acceptance Testing (UAT) | [5 empty] | 0
| The 37 Respondents: Selecting a representative mix of 3rd/4th-year BSIT/BSEMC students and faculty. | Canoy, Chijay |  |  |  | 0%
| Task-Based Testing: Providing specific scenarios (e.g., "Student: Create a team and upload Chapter 1") to ensure the UI is intuitive and the logic is sound. | Canoy, Chijay |  |  |  | 0%
| Defect Logging: Categorizing every "I'm confused" or "This button didn't work" into a severity log to fix critical issues before the final defense. | Canoy, Chijay |  |  |  | 0%
| User Acceptance Testing (UAT) | [5 empty] | 0
| The Framework: Mapping your system to characteristics like Functional Suitability, Performance Efficiency, and Usability. | Canoy, Chijay |  |  |  | 0%
| Quantitative Analysis: Using Likert-scale data to calculate weighted means, giving you a scientific "Quality Score." | Canoy, Chijay |  |  |  | 0%
| Final Archiving & Handover | [5 empty] | 0
| Ensuring the project lives on after you graduate. | Antipuesto, Throylan |  |  |  | 0%
| The "Vault" Seal: Verifying the "FINAL_APPROVED" workflow, where manuscripts become read-only, permanent artifacts. | Antipuesto, Throylan |  |  |  | 0%
| Knowledge Transfer: Writing the Administrator Guide for the Capstone Coordinator so they can manage the system without you. | Antipuesto, Throylan |  |  |  | 0%
| Infrastructure Handover: Securely transferring the keys to the kingdom—credentials for MongoDB Atlas, Render, Vercel, and Google Cloud—to the department. | Añedez, Patrick Josh |  |  |  | 0%
| Manuscript & Final Defense | [5 empty] | 0
| Chapter 4 & 5: Writing the "Results and Discussion" (how it performed) and "Conclusions" (what we learned). | Antipuesto, Throylan |  |  |  | 0%
| BukSU Formatting: Applying the final polish to margins, citations, and front matter to meet the university's strict guidelines. | Antipuesto, Throylan |  |  |  | 0%
| The Big Day: Rehearsing the demo to perfection, anticipating panel questions, and finally securing those signatures on the approval sheet. | Antipuesto, Throylan |  |  |  | 0%
Prepared by: |  |  | Noted by: |  |  |  |  | WEEK 1 T: Approved by:
| Añedez, Patrick Josh | Antipuesto, Throylan |  | GLAIZA MAE A. LIBE |  |  |  | WEEK 2 M: Dr. Sales G. Aribe Jr.
| Researcher | Researcher |  | Adviser |  |  |  | WEEK 2 M: Instructor
| Bautista, Steven Joe | Canoy, Chijay
| Researcher | Researcher